## Template Plan
| DEI Strategic Planning Template from September 15, 2020 program led by Marisa Santoro | marisa@inrshoes.com
Mission / Vision | Metric
▪Create diversity and inclusion statements/guiding principles
▪Schedule staff and board discussions on topic of DEI | Lock-in 8 combined monthly and quarterly meetings for next 6 months.
▪Develop an organizational DEI future state
▪Set concrete DEI goals and benchmarks
▪Select and Schedule Executive Leadership / Steering Committees | Lock-in 12 monthly meetings for next 6 months.
Governance / Policies | Metric | DEI is embedded in all company policies and procedures.
▪ Create an equity policy or statement
▪ Define DEI Language to be used
▪ Explore 'where are we playing it safe?'
▪ Increase Board Diversity | 40% increase in diverse members, 15% bi-lingual, bi-cultural
Create and define the position.
Post online. Leverage LinkedIn target profile search in diverse sectors.
Ask current board members for referrals.
Consider project-based involvement versus ongoing to avoid lengthy time commitment.
Obtain a legal review before you post online.
Blast to your contacts, e-mail, social media accounts
Ask neighbouring organizations who have more board diversity about their strategies.
Identify events that attract the type of people you’re looking to recruit.
▪Set DEI Agenda | Feedback from assessments placed side by side to the quantitative data. Workplace patterns and issues become evident and help prioritize the D&I agenda in terms of which areas to address and respond to first.
▪Schedule DEI into Budget Planning
Research, Data and Analytics | Metric | Diverse perspectives are engaged and valued, relationships are valued and there is a culture of respectful transparency and feedback
▪Distribute Diverse Baseline Self-Assessments | Just how diverse are we?
Race | # of employees in supervisory and management positions across demographic factors.
Gender
Age
Physical Disability
Sexual Orientation
▪Distribute Inclusive Baseline Assessments | Having a pulse on the inclusiveness of the culture gives a solid snapshot of where your organization is as a whole, and is also a key driver to measuring the program’s success as it moves forward.
Questions on environment, family-friendly policies, workplace culture, are they being encouraged to pitch their ideas, do they feel accepted when they agree to disagree with their supervisors? Do they receive the same respect as others? Do they feel valued? Project Assignments? | What would you have to see happening and stop happening to know that inclusion is present?
▪Develop Monitoring Mechanisms
▪Establish Accountability | Periodic # of E-mails, Presentations Disseminating data which require follow-up
Workforce Diversity | Metric | You practice accessible and equitable recruitment, retention and advancement and reflects diversity at all levels of your organization.
▪Recruitment Strategies | +20% increase in bilingual and bicultural staff
Revisit Interview process
Revisit retention strategy
Redefine the selection criteria. Lower the bar. Someone who "makes themself indispensable", carries weight in terms of being a successful hire.
Incorporate DEI into staff work plans
Incorporate DEI into performance evaluations
New Hire Welcome Event and/or Announcements | 2x a month
▪New Hire Onboarding & Orientation | Integrating DEI
▪Training and Awareness (Board and Staff) | Understanding of the issues at all levels of the organization. Gap analysis and crucial feedback from assessments should drive the training topics delivered, be discussed and finalized with council members and ERG leads. Training and delivery would typically we structured in such a way to be a building block of modules rolled out in sequence, effectively creating a custom leadership curriculum based on where the current needs are, keeping in mind there can be different growth tracks at various levels and roles in the organization. For example, the data may highlight that overall those in managerial roles require more soft skill training where an emphasis on communication would weigh heavier than those in analyst or administration roles where more collaboration skills are required.
Develop Curriculum | e.g. Cultural Sensitivity Training, Conflict Resolution
Distribute DiSC Assessments | Employee Strengths(Dominance, Influence, Steadiness, Conscientiousness
▪Create Leadership Development Opportunities | 1 Program every Quarter with Consultant,Trainers
Workshops
Seminars
Webinars
Q&A Phone Sessions
Peer Mentoring
Coaching
Online Courses
Networking Events
Train-the-Trainer
▪Hold Internal Events that support Inclusion
▪Create Decision-Making Opportunities
▪Establish Mechanisms for Support and Resources
Web Form | Confidentially log incidents
E-mail Inbox | # Concerns and Issues, #HighPriority
Marketing / Branding | Metric | You have created an atmosphere of inclusion that leverages the creativity and connection diversity can bring, to uphold exceptional levels of service.
▪Publish Branding Communication Toolkit. Does the language need to change?
▪If your nonprofit were a book, what would its title be? Why would others want to read it?
▪Frame the message. Don't have to explicitly call it DEI. Subtle advertisting.
▪Substitute the WHAT message with a WHY message speaking to the impact of your organization. i.e. an Impact Statement.
▪Answer how are we RELEVANT?
▪Assess Community Needs and Motivators
▪Develop a DEI Platform
▪Create / Magnify an Online Presence (website, social media) | % Increase in fan base / Followers
Technical Resources (Infrastructure, Translation, Video Services)
Responding to National Crisis, Injustices; Sharing Opinions
▪Send Direct Mailings | # Mailings a week
▪Contribute to Local Newspapers
▪Announce Promotional Partnerships that Serve your DEI Mission
▪Engage DEI Conversations | % Article Contribution, Opinion Piece, Interviews
Social Responsibility | Metric | You utilize community partnerships that empower historically underserved communities to be drivers of equity within their own communities.
▪Conduct Equity Evaluation and Impact Assessments | Establish metrics collected from constituent feedback on your organization from a DEI perspective
Access to and Equity of Services
Cultural Events | #Target programs in geographic areas where the greatest inequities exist
Multi-Lingual Services
Hearing Impaired
Translated Materials and Interpreters
▪Create Community Engagement Programming
Virtual Opportunities
Open-ended Call for action to get experts involved, offering their services.
Attracting non-traditional groups to your NP through partnerships, achivement more accessibility.
Events/Concerts/Education
▪Perform consistent Outreach and Communication | #Broadcasts from Newsletter, #Opens, #Clicks
▪Create Support Communities
Empower Young Ambassadors
Blogging Platform (low maintenance, quick win and still controlled)
Build Virtual/Online Communities
▪Develop Community Partnerships
Outreach to local organizations
Share Resources
Supplier Diversity | Metric | You have a solid diverse supplier base.
▪Review contracting policies
▪Vendor selection - M/WBE | %Women-Owner, %Disabled, %Minorities
▪Review Procurement contracts
Note on A30: As the D&I program is formally stood up, avoid a top-down approach ,as it can potentially risk leaders to being tone deaf to valid employee concerns around an inclusive culture.
Note on A73: Response rates to direct mail can be 10x higher those of digital marketing.
Note on A77: Community Impact